We are pleased to inform you that Plejades Bulgaria Ltd has successfully completed all activities and has achieved the anticipated results of the grant agreement under the Operational Programme "Human Resources Development" 2014-2020, under procedure BG05M9OP001-1.003 "New Workplace 2015" with a total value of 91 065.76 BGN. Contract period - 19.05.2017 to 18.11.2018.

The project "Opening of new jobs in Plejades Bulgaria Ltd." is realized with the financial support of the European Social Fund to the European Union and includes in total five activities.

**For activity 1 "Recruitment and hiring of unemployed and / or inactive persons for a period of up to 12 months"** 6 contracts were signed with unemployed and inactive persons including such aged between 30 and 54, over 54, and unemployed and inactive young people up to 29 years. Approved persons from the eligible target group have been employed under a labor contract for a period of 12 months, and after the completion of the project, 50% of the employees have renewed their contracts for another 12 months.

**For activity 2 "Providing training to key competences under the European Qualifications Framework on Key Competences under the European Qualifications Framework: Key Competence 2 "Communication in foreign languages "**, the target group members have successfully completed English language training at A1, A2 and B1 levels as per approved Curriculum.

**For activity 3 "Purchase of equipment related to the creation of new jobs"** and in order to ensure a qualitative and professional performance of their duties, the new workplaces were provided with new computers and other office equipment which is insured for a period of 1 year, as well as with specialized software for designing and specialized building software.

**As a result of activity 4 "Project Management"** procedures were carried out and all Contracts with contractors for delivery of equipment, specialized software for designing, specialized building software, materials for visualization, publicity, insurance for 1 year, labor medicine and English language training were concluded.

**For activity 5 "Information and Publicity**", materials for visualization and published publication on the progress of the project in "Sega" newspaper on 06.02.2018 were produced and delivered with the funds provided under the project.

As a final activity on the project "Plejades Bulgaria" Ltd. organizes an information meeting, which will present the results of the implementation of the project and the effects that have been achieved as a result of its implementation. The meeting will take place on 09.11.2018. from 10 a.m. in the conference hall of Plejades Bulgaria Ltd. at 45 “Bregalnitsa” Street, fl.3, Sofia, Bulgaria.